## Slide 1: CTL BRD Status Update
Phase | Completion | Status
Requirement Gathering | Completed | In Progress
BRD | In Progress | In Progress
Progress / achievements in the last week
Disconnection Orders: Functional steps captured & Draft BRD shared with development team New Install & New BAN: Functional steps captured & Draft BRD shared with Ops Reterm & Renewal: WIP
Activities planned for this week
Document the functional steps for Reterm/Renewal & Add/change/remove bundle Ops SMEs to attach the screenshots in the completed BRDs
Weekly Update: | 10th December, 2019
Function: | CTL
Major decisions made in the last week
Ops in unison with the solution (Template) which would require manual intervention New Install & BAN – Standardization of the OTC Handbook is required PoC needs to be done by Dev. Team to check app & process feasibility
Major decisions for this week
Approval for documents sharing pending
Key Issues |  |  | 
Issue | Status | Raised Date | Resolved Date
Yet to get approval for sharing of Docs required for BRD | Open | 4-Nov-2019 | NA
Infra not yet procured | Open | 4-Nov-2019 | 
Key Risks |  |  | 
Risk | Status | Mitigation | Closed Date
Development cannot start without client approval | Open | None | NA
Development cannot start with an incomplete BRD | Open | None | NA